## Hoja 1
INCR-1 | SUBSYSTEMS | FP | WORKING DAYS | %
| TM | 83 | 117.333 | 63.4919
| MS | 48 | 67.467 | 36.5081
|  | 131 | 184.8 | 100
INCR-2 | MMANAG | 64 | 98 | 50.308
| MMAKING | 68 | 96.8 | 49.692
|  | 132 | 194.8 | 100
INCR-3 | SM | 26 | 38.133 | 100
|  | 26 | 38.133 | 100
INCREMENT 1 | ACTIVITIES | % PHASE | % ACTIVITY | WORKING DAY ACTIVITY
Analysis |  | 20 |  | 36.96
Req.Specification |  |  | 67 | 24.7632
Prototyping |  |  | 33 | 12.1968
Rev. Analysis |  |  | 0 | 0
Design |  | 20 |  | 36.96
D.SubTM |  |  | 63.4919 | 23.4666
D.SubMS |  |  | 36.5081 | 13.4934
Rev. Design |  |  | 0 | 0
Coding |  | 15 |  | 27.72
C.SubTM |  |  | 63.4919 | 17.5999
C.SubMS |  |  | 36.5081 | 10.1201
Unit Testing |  | 15 |  | 27.72
UT-SubTM |  |  | 63.4919 | 17.5999
UT-SubMS |  |  | 36.5081 | 10.1201
Integration Testing |  | 20 |  | 36.96
Int.Task |  |  | 100 | 36.96
Rev.Integration |  |  | 0 | 0
Installation |  | 10 |  | 18.48
Technical Installation |  |  | 67 | 12.3816
Acceptance |  |  | 33 | 6.0984
Rev. Installantion |  |  | 0 | 0
TOTAL |  |  |  | 184.8
INCREMENT 2 | ACTIVITIES | % PHASE | % ACTIVITY | WORKING DAY ACTIVITY
Analysis |  | 20 |  | 38.96
Req.Specification |  |  | 67 | 26.1032
Prototyping |  |  | 33 | 12.8568
Rev. Analysis |  |  | 0 | 0
Design |  | 20 |  | 38.96
D.SubMMANAG |  |  | 50.308 | 19.6
D.SubMMAKING |  |  | 49.692 | 19.36
Rev. Design |  |  | 0 | 0
Coding |  | 15 |  | 29.22
C.SubMMANAG |  |  | 50.308 | 14.7
C.SubMMAKING |  |  | 49.692 | 14.52
Unit Testing |  | 15 |  | 29.22
UT-SubMMANAG |  |  | 50.308 | 14.7
UT-SubMMAKING |  |  | 49.692 | 14.52
Integration Testing |  | 20 |  | 38.96
Int.Task |  |  | 50.308 | 19.6
Rev.Integration |  |  | 49.692 | 0
Installation |  | 10 |  | 19.48
Technical Installation |  |  | 67 | 13.0516
Acceptance |  |  | 33 | 6.4284
Rev. Installantion |  |  | 0 | 0
TOTAL |  |  |  | 194.8
INCREMENT 3 | ACTIVITIES | % PHASE | % ACTIVITY | WORKING DAY ACTIVITY
Analysis |  | 20 |  | 7.6266
Req.Specification |  |  | 67 | 5.1098
Prototyping |  |  | 33 | 2.5168
Rev. Analysis |  |  | 0 | 0
Design |  | 20 |  | 7.6266
D.SubMMANAG |  |  | 100 | 7.6266
Rev. Design |  |  | 0 | 0
Coding |  | 15 |  | 5.7199
C.SubMMANAG |  |  | 100 | 5.7199
Unit Testing |  | 15 |  | 5.7199
UT-SubMMANAG |  |  | 100 | 5.7199
Integration Testing |  | 20 |  | 7.6266
Int.Task |  |  | 100 | 7.6266
Rev.Integration |  |  | 0 | 0
Installation |  | 10 |  | 3.8133
Technical Installation |  |  | 67 | 2.5549
Acceptance |  |  | 33 | 1.2584
Rev. Installantion |  |  | 0 | 0
TOTAL |  |  |  | 38.133