## Slide 1: Risks Planning and Management
Made by: Jorge Blanco Rey
Ángel Casanova Bienzobas
Rodrigo Juez Hernández
Pablo Soëtard García
Group: 2391, team 2

## Slide 2: RISK IDENTIFICATION
Risk ID | Name | Risk description | Category
R1 | Lack of time | We must start a new project on the same deadline of the UAM project which could cause that, if the planning established was not fulfilled due to any inconvenient, a potential lack of time to finish the UAM project may occur. | Project
R2 | Low Quality | Having programmers that are unexperienced with this type of application, and with underlying technical architecture, may affect the quality of the project. Also, since we are going to subcontract other companies, this can affect the quality if they do not understand well the project, or if coordination problems happen. | Personnel Management Development
R3 | Lack of Coordination | It is expected to subcontract UAMSOFT Systems and SOFTCOM. The companies may work in an independent way and will affect the coordination of the project. | Project External Sources

## Slide 3: RISK IDENTIFICATION explanations
R1:
  It is a project related risk because it directly attains to the integrity and feasibility of the project in the time stipulated, since there is a new one that it is crucial for the subsistence of the company that may require more time that the one already allocated for it.
R2:
  The second risk is related to the Personnel Management and Software Development, because it involves the personnel of the company not being up to date on the technical knowledge needed for the project and thus it can affect to the software development too. Also, there could be interaction problems between the project personnel and the one of the subcontracted company.
R3:
  The third one relates to the Project and External Sources category, because the correct project conclusion depends on the subcontracted companies which are external sources and may potentially have coordination problems.

## Slide 4: RISK ESTIMATION
Risk ID | Name | Likelihood | Impact Factor
R1 | Lack of time | High 0.8 | Very High 0.9
R2 | Low Quality | High 0.7 | Medium 0.6
R3 | Lack of Coordination | Medium 0.5 | High 0.8
Note: The justifications of likelihood and impact factors will be explained on the next slides

## Slide 5: RISK ESTIMATION explanations
R1
  Risk identification
    Likelihood: 0.8
      The deadlines of both, the TEAMTEAM application and the new project are set, so the company will probably prioritize on this new one since it is crucial for the future of the project.
    Impact factor: 0.9
      If this risk happen, it is going to affect too much the TEAMTEAM project, since most of the time it is going to be dedicated to this new project.

## Slide 6: RISK ESTIMATION explanations
R2
  Risk identification
  Likelihood: 0.7
    Due to technical personnel rotation and programmers do not have a high experience neither in the applications nor the underlying technical architecture.
  Impact factor: 0.6
    In case technical staff are unable to build the application the training and help will require more time, personnel and costs.

## Slide 7: RISK ESTIMATION explanations
R3
  Risk identification
    Likelihood: 0.5
      Subcontracted companies will participate in the project development, software updates and product licenses, so there can be problems with the coordination and the understanding of the project. This problems can be avoidable and may not happen, if there is a person who controls that the new companies are integrated correctly.
    Impact factor: 0.8
      If this risk happen, it is going to affect the UAM cycles project, since if coordination problems happen may be incompatibilities with the parts developed by each one, or if the new company does not understand the project all they develop could be useless.

## Slide 8: RISK ASSESSMENT
Risk ID | Short name | Risk Exposure | Priority | Breaking points
R1 | Lack of time | 0.72 | 1 | When the estimated time is exceeded by more than 10%
R2 | Low Quality | 0.42 | 2 | More than the 70% of the personnel had not gotten familiar with the actual environment in 25% of the allocated time for the project
R3 | Lack of Coordination | 0.4 | 3 | UAMSOFT does not deliver on more than 85% of the requirements or SOFTCOM does not handle more than 65% of licenses and updates.

## Slide 9: BREAKING POINT EXPLANATIONS
R1
  Due to the incoming project that is crucial for the company, it cannot be afforded to expand the time spent on the UAM project more than 10%, because this could affect to the accomplishment of the other project that is more important for the company.
R2
  If in the 25% of the time that the programmers have to do their task 70% of them do not already know how to do it, the project leader must handle the situation since the software they have done probably up to that point is of low quality.
R3
  If more than the 85% of the requirements are not met, there would not be enough time adapt the software to the customers specifications and the best option in that case is to halt the whole project. The same situation will be reached if more of the 65% of the code does not handle the license and updates. The extra time expended will not be worth for the company.

## Slide 10: RISK MANAGEMENT - PREVENTIVE ACTIONS
Risk ID | Short name | Preventive actions
R1 | Lack of time | Follow the Gantt diagrams strictly. Monitor both projects for having a perspective of the available personnel for this project in the future. Collect some CV in order to have a quick access to extra personnel.
R2 | Low Quality | Perform tests to the developers in order to make them getting familiar with the main libraries. Assing a mentor to the developers that have lower experience. Send the developer to a sort course before starting with the project.
R3 | Lack of Coordination | Make a written and close contract with all requirements that those companies shall accomplish. Choose companies whose reviews are positive or those ones with have worked with us previously. Ask the subcontracted companies to dispatch us a Gantt diagram of their internal implementation.

## Slide 11: RISK MANAGEMENT – CORRECTIVE ACTIONS
Risk ID | Short name | Corrective or mitigation actions
R1 | Lack of time | Hire new personnel and adjust the remaining effort. Redesign the project plan. Work on the weekends.
R2 | Low Quality | Hire an expert in the environment for leading the personnel wit lower experience. Implements the "pair programing" method to allow developers to help each other. Orde an expert to make a quality test of the software in order to see if the product is valid to be dispatched. Audit the company to find out why the quality was lower, and how to prevent inexperienced technical staff.
R3 | Lack of Coordination | Have and alternative company in case one of them left the project in the development phase. Update the Gantt chart, not setting very “caught” dates, in case some problems arise. Promote a person as a manager to merge all the modulus that the third parties has provided to the project